Detailed Scope of Work — Single-Vendor E-Commerce Platform (Web + Android + iOS)
Client: TBD
Date: 11 Oct 2025
Scope Version: v1.3 (Comprehensive Multi-Platform Scope)

### 1. Project Overview

The objective of this project is to design, develop, and deploy a complete single-vendor e-commerce ecosystem — consisting of a Website, Android Application, and iOS Application — under one unified technology framework. The platform will deliver a secure, scalable, and engaging shopping experience for customers while providing a comprehensive admin panel for business management.

This solution uniquely integrates two advanced engagement models —

- Entertainment (MCQ Refund Model): Users can earn cashback by participating in quizzes after purchase.

- ROI Plan (Scheduled Cashback): Offers structured monthly returns based on user-selected plans.

Additionally, the system introduces a 5-Level Referral System, enabling users to earn referral rewards from their network up to five levels deep, creating a community-driven ecosystem.

Technology Stack:

- Frontend (Web): HTML, CSS, JavaScript

- Mobile (Android/iOS): Flutter

- Backend: Laravel + MySQL

- Hosting: Shared Hosting

- Integrations:Razorpay / Stripe / PayPal / Flutterwave

### 2. Project Objectives

- Build a cross-platform single-vendor e-commerce system optimized for performance, scalability, and user engagement.

- Deliver a centralized admin panel for catalog, user, wallet, order, and referral management.

- Ensure seamless integration between Web, Android, and iOS using shared APIs.

- Introduce gamified refund (MCQ) and ROI cashback modules for retention.

- Integrate a multi-tier (5-Level) Referral System to boost organic growth.

- Ensure data security, KYC verification, and regulatory compliance (PPI, GDPR, Indian IT norms).

### 3. Scope of Work (Detailed)

#### 3.1 Customer-Facing Modules (Web + Android + iOS)

3.1.1 User Experience & Interface : 15 hour

- Responsive and consistent UI across all devices.

- Dynamic homepage with rotating banners and featured products.

- Light/Dark mode compatibility in mobile apps.

- Multilingual support (optional).

3.1.2 Authentication & Profile Management : 20 hour

- Registration via email, OTP, or Google login.

- Secure JWT-based login.

- KYC verification for withdrawals.

- Two-factor authentication for sensitive actions.

3.1.3 Product Catalog& Navigation : 10 hour

- Multi-level categories and filters.

- Product detail pages with ratings, reviews, and stock visibility.

- SEO-friendly product URLs.

3.1.4 Cart, Checkout & Payments : 45 hour

- Add to cart, wishlist, and compare features.

- Address management and real-time delivery charge calculation.

- Coupon code system.

- Payment integrations: Razorpay, PayU, Stripe, PayPal, Flutterwave.

- Webhook-driven success/failure handling.

3.1.5 Entertainment Module (MCQ Refund Flow) :50 hour

- Post-purchase quiz feature.

- Admin-defined question pool and pass percentage.

- Anti-cheat logic (IP/device tracking).

- Automatic cashback on success.

3.1.6 ROI Plan Module (Scheduled Cashback)  : 80 hours

- Multiple tenure options (6–60 months).

- Auto-credit monthly cashback to wallet.

- Ledger with ROI schedule and early termination logic.

3.1.7 Wallet System : 70 hour

- Unified wallet for refunds, ROI, and referrals.

- Ledger with transaction references.

- Wallet use at checkout.

- Withdrawal requests post-KYC.

3.1.8 Referral System (5-Level) : 70 hour

- Unique referral code and link.

- 5-level deep commission logic.

- Referral earnings to wallet.

- Admin control for rates and fraud prevention.

3.1.9 User Dashboard : 60 hour

- Order and ROI tracking.

- Quiz results and referral income.

- Wallet ledger and withdrawal requests.

3.1.10 CMS & Support Pages : 5 hour

- Contact form, FAQs, terms, and policy pages.

#### 3.2 Admin Panel (Web-Based)

3.2.1 Dashboard & Role-Based Access : 10 hour

- Real-time KPIs: GMV, orders, wallet liability, ROI exposure.

- Roles: Super Admin, Finance, Marketing, Support, Compliance.

3.2.2 Catalog Management : 15 hour

- Product CRUD, stock management, bulk uploads.

- Price, SEO tags, and visibility control.

3.2.3 Order & Logistics Management : 40 hour

- Order filtering and manual order creation.

- Refunds, returns, and invoice generation.

- Integration with Shiprocket/Delhivery/Xpressbees.

3.2.4 Quiz & ROI Management : 40 hour

- Question bank, campaign setup, pass/fail analytics.

- ROI plan configuration with duration and credit schedules.

3.2.5 Referral & Wallet Management : 40 hour

- Track 5-level referrals and payouts.

- Adjust commission percentages.

- Manual wallet adjustments with logs.

3.2.6 Compliance & KYC : 30 hour

- Document verification using PAN/Aadhaar APIs.

- Risk scoring and audit history.

3.2.7 CMS & Notification Management : 20 hour

- Manage banners, FAQs, and popups.

- Push notifications (Firebase).

### 4. Integrations

- Payment Gateways:Razorpay, Stripe, PayPal, Flutterwave

- Payout Partners:RazorpayX / Cashfree

- Shipping Partners:Shiprocket, Delhivery, Xpressbees

- Email/SMS: SendGrid, MSG91, Twilio

- Analytics: Google Analytics 4, Firebase Analytics

### 5. Testing & Quality Assurance : 30 hour

- Unit, integration, and user acceptance testing.

- Stress testing for high-traffic events.

- Security validation (OWASP ASVS).

### 6. Deployment & Infrastructure : 20 hour

- Hosted on Shared Hosting Environment.

- GitHub-based version control.

- SSL setup and auto-backups.

### 7. Project Timeline (16–20 Weeks)

| Phase | Duration | Deliverables |
| --- | --- | --- |
| Discovery & Wireframing | 2 Weeks | Requirements & UI/UX design |
| Development Phase 1 | 4 Weeks | Web modules: catalog, checkout, payments |
| Development Phase 2 | 4 Weeks | Admin, wallet, ROI, referral modules |
| Mobile Development | 4 Weeks | Android & iOS integration |
| Testing & Optimization | 3 Weeks | QA, load test, UAT |
| Deployment & Training | 1 Week | Hosting setup, documentation, handover |

### 8. Payment Terms

| Milestone | % | Description |
| --- | --- | --- |
| Project Kick-off | 30% | Requirement sign-off and design approval |
| Phase 1 Completion | 25% | Web module completion |
| Phase 2 Completion | 25% | Admin & wallet completion |
| Mobile Apps Completion | 10% | Android & iOS delivery |
| Final UAT & Go-Live | 10% | Deployment & acceptance |

### 9. Costing Structure (Indicative Framework)

| Component | Description | Cost (₹) |
| --- | --- | --- |
| Web Platform | HTML + Laravel development | Included |
| Android App | Flutter build & integration | Included |
| iOS App | Flutter & integration | Included |
| Admin Panel | Business management console | Included |
| Integrations | Payment, logistics, and analytics | Included |
| Testing & QA | Manual testing | Included |
| Deployment & Training | Shared Hosting & handover | Included |
| AMC (Optional) | Annual maintenance & feature updates | Additional |

(Inclusive of Web + Android + iOS + Admin Panel Development)

### 10. Warranty & Support

- Warranty Period: 60 days post-launch bug fixing.

- Support Scope: Issue resolution, uptime monitoring, and minor UI tweaks.

- AMC (Optional): Extended upgrades and maintenance support.

### 11. Exclusions

- Multi-vendor marketplace features.

- Third-party license or subscription fees.

- Content creation, photography, or branding.

- Legal or policy documentation drafting.

- Hosting/domain renewals beyond setup.